OFFICE OF THE POLICE & CRIME COMMISSIONER FOR SURREY & SURREY POLICE
Internal Audit Progress Report December 2024

Contents:
1. Purpose of report	3
2. Performance dashboard	4
3. Analysis of ‘Live’ audit reviews	6
4. Rolling work programme	8
Purpose of report
Internal audit reviews culminate in an opinion on the assurance that can be placed on the effectiveness of the framework of risk management, control and governance designed to support the achievement of management objectives of the service area under review.
CIPFA have recommended standardising the terminology and definitions used in internal audit engagements across the whole of the public sector and have published a standard set of opinions and supporting definitions for internal audit service providers to use. To ensure we continue to conform to the best practice principles, we have adopted the standard definitions. The assurance opinions are categorised as follows:

* Some reports listed within this progress report (pre 2020/21 audit plan) refer to categorisations used by SIAP prior to adoption of the CIPFA standard definitions, reference is provided at Annex 1.

Performance dashboard

0%
Complete
7% of revised
plan delivered to to least draft report
61%
Work in Progress
39%
Yet to Commence
Stakeholder Satisfaction Survey Results
100%
98%
96%
94%
92%
90%
88%
86%
84%
Target
Actual

Days Delivered

	Surrey 2024/25 plan	Joint Sussex and Surrey / 2024/25 plan
Original Plan Days	103	350
Revised Plan Days	103	350
Days delivered	59	121
Percentage of revised / plan delivered	57%	35%

Compliance with Public Sector Internal Audit Standards
An External Quality Assessment of the Southern Internal Audit Partnership was undertaken by the Institute of Internal Auditors (IIA) in September 2020. The report concluded:
‘The mandatory elements of the IPPF include the Definition of Internal Auditing, Code of Ethics, Core Principles and International Standards. There are 64 fundamental principles to achieve with 118 points of recommended practice. We assess against the principles.
It is our view that the Southern Internal Audit Partnership conforms to all 64 of these principles.
We have also reviewed SIAP conformance with the Public Sector Internal Audit Standards (PSIAS) and Local Government Application Note (LGAN).
We are pleased to report that SIAP conform with all relevant, associated elements.’
Analysis of ‘Live’ audit reviews (as at 21 November)
Audit Review	Report Date	Audit Sponsor	Assurance Opinion	Total Management / Action(s)	Not Accepted	Not Yet Due	Complete/ Retired**	Overdue
								L	M	H
IT Virtualisation	May 22	CDIO	Limited	8	0	0	6		2
ERP – Legacy IT Risks Oracle People Solutions	Sep 22	CDIO	No Assurance	11	0	0	5			6
Strategy and arrangements for delivery of training to meet future / need	Aug 22	DPS	Reasonable	4	0	0	3		1
Duty Resource Planning	Sep 22	ACC	Limited	9	0	0	8		1
Operating Systems Management	Dec 22	CDIO	Limited	17	0	0	16		1
Vulnerability Management	Jul 23	CDIO	Reasonable	12	0	0	11	1
Database Management	Sep 23	CDIO	Limited	21	0	0	19		2
SSP Vehicle Recovery Process	Jan 24	ACC	Limited	11	0	0	9	2
SSP Armouries (storage and / management)	Feb 24	ACC	Limited	13	0	3	10
SSP Business Continuity (SAP/ Oracle)	Feb 24	CFO (CC)	Limited	14	0	0	12	1	1
Surrey Payroll	Feb 24	CFO (CC)	Reasonable	5	0	1	4
SSP Government Procurement Cards*	Apr 24	CFO (CC)	Limited	4	0	0	4
Surrey RoadSafe Partnership	Apr 24	ACC	Reasonable	11	0	0	4	2	5
SSP Estates and Facilities Management	May 24	CFO (CC)	Limited	16	0	3	6		3	4
SSP Contract Management - Capital	May 24	CFO (CC)	Reasonable	3	0	1	2
SSP Redundancy Process and / Payments	May 24	DPS	Limited	8	0	0	7			1
SSP IT Major Incident Management	Jun 24	CDIO	Reasonable	6	0	4	1		1
SSP Learning & Development / Mandatory Training 2023/24	June 24	DPS	Limited	6	0	5	1

SSP Flexible Retirements	Jun 24	ACC	Reasonable	10	0	0	8		1	1
Surrey Perpetrator Pathways – Domestic Abuse – Governance and / Roles & Responsibilities	Jul 24	ACC	Reasonable	3	0	0	0		3
SSP Supply Chain Security / Management	Jul 24	CD&IO	Reasonable	14	0	4	10
Surrey - Data Storage and Backup	Jul 24	CD&IO	Reasonable	5	0	3	1		1
SSP Data Protection Impact / Assessments	Oct 24	DCC	Reasonable	8	0	8	0
Total								6	22	12

* Denotes audits where all actions have been completed since the last progress report.
** Denotes where actions are retired/pending retirement.

Audit Sponsor (Director)
Chief Finance Officer	CFO
Deputy Chief Constable	DCC
Assistant Chief Constable	ACC
ACO Chief Digital Information Officer	CDIO
ACO Director People Services	DPS

Rolling Work Programme
# 2023/24 Audit Plan – Remaining Audits

Audit Review	Audit Sponsor	Scoping Terms of / Reference Issued	Fieldwork Draft / Report Issued	Final Report Issued	Assurance Opinion	Comment / Previous Opinion
Shared Plan with Sussex Police
Data Protection Impact Assessments	DCC	 	12.08.24	17.10.24	Reasonable
Legacy Application Management	CD&IO	 	20.11.24			Delayed due to auditor absence. / First review

2024/25 Audit Plan

Audit Review	Audit Sponsor	Scoping	Terms of Reference / Issued	Fieldwork	Draft Report / Issued	Final Report / Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Collaborated Plan
Use of Air Support (Drones) - Governance	ACC	17.06.24	02.08.24	04.11.24				Q1	Fieldwork underway, delayed due to auditor availability. / First Review
NPAS - National Air Helicopter Service – Use of Allocated	ACC	02.08.24	09.09.24	07.10.24 / 18.11.24				Q2	Close of audit meeting 5 Dec. / First Review
Hours
Management of Fleet Vehicles	CFO	01.08.24	05.08.24	09.09.24 / 18.11.24	15.11.24			Q2	Expecting management actions w/c 9 Dec.

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
2019-20 -Limited and 2021-22 Reasonable
Health and Safety	DCC	17.10.24			Q2				Requested by Force to move to Q4 due to clash with a H&S Investigation. / 2021-22 – Reasonable and 2023-24 Reasonable
Transformation Savings Governance	CFO	31.07.24	18.09.24		Q2				Delayed due to auditor availability. Detailed scoping meeting 26 Nov. / First Review
Crime Management – Organised Crime Groups Processes	ACC	27.08.24	09.09.24	17.10.24	Q2				Proposed increase in audit days following detailed scoping meeting. Close of audit meeting booked for Dec. / First Review
Business Continuity Planning	DCC	24.10.24			Q3				Scoping meeting 4 Nov, draft ToR issued 26 Nov. / 2020-21 -Reasonable and / 2023-24 - Limited
Counter Fraud Work / - Advisory	ACC	28.10.24			Q3				Scoping meeting being arranged / First Review

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Dog School – Income Generation	ACC							Q3	Resources allocated, commencing scoping. / First Review
Armouries – Storage and Management	ACC							Q4	2023-24 - Limited
Recruitment	DPS	14.11.24						Q4	Moved to Q3 to accommodate H&S being moved to Q4. / Scoping 28 Nov. / 2020-21 - Reasonable
Duty of Care Risk Assessments	ACC							Q4	First Review
Estates and / Facilities – Recovery Plans	CFO							Q4	First Review
Joint Procurement	CFO							Q4	2020-21 - Reasonable
Collaborated Plan - IT
Software Licensing	CD&IO	07.06.24	22.08.24					Q1	Draft ToR issued 22 Aug / First Review
Service Transition	CD&IO	21.06.24	05.09.24					Q1	Draft ToR issued 5 Sept / First Review
IT Disaster Recovery and IT Service Continuity	CD&IO							Q2	Scoping being rescheduled due to auditor sickness. / First Review

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
Data Centre Facilities and Security	CD&IO							Q2	Resources allocated, looking to commence scoping. / First Review
Application Management NICE / Investigate	CD&IO							Q3	Resources yet to be allocated / First Review
High Privilege Access Management	CD&IO							Q3	Resources allocated, looking to commence scoping. / First Review
IT Health Check Remediation	CD&IO							Q4	First Review
Surrey Plan
Estates Strategy - Redevelopment of / Mount Browne	CFO	14.05.24	02.07.24	08.10.24				Q1	Testing underway. / 2021-22 -Substantial
Management Information – dashboard / development and use	DCC	20.05.24	22.08.24	23.09.24 / 24.10.24	13.11.24			Q1	Close of audit 12 Nov. / First review
Missing Person Compliance	ACC	23.05.24	18.06.24					Q1	Delayed due to auditor sickness and change of staffing at Force. Detailed scoping 31 Oct. / First review

Audit Review	Audit Sponsor	Scoping	Terms of / Reference Issued	Fieldwork	Draft / Report Issued	Final / Report Issued	Assurance Opinion	Quarter	Comment / Previous Assurance Opinion
									Scoping meeting initially
									arranged for the 15 Aug, been
Violence Against / Women and Girls - relentlessly pursuing offenders	ACC	10.09.24	08.10.24					Q2	cancelled by the Force several times. Re-arranged for 26 Sept. Removed from SSP plan / to Surrey plan 1.10.24.
									First Review
Right Care, Right Person	ACC	28.10.24						Q3	Scoping meeting 12 Nov. / First review
PCC General and Statutory Duties – Assurance	CFO (OPCC)	04.11.24						Q3	Scoping meeting 14 Nov. / First review
Framework
Adult Abuse Investigation – Governance and / Reporting	ACC							Q4	First review

The following variations have been made to the 2024/25 internal audit plan since it was presented to the Joint Audit Committee in April 2024 and changes since the last JAC meeting are marked with *.

Collaborated Plan
Audit reviews removed from the plan
Violence Against Women and Girls - relentlessly pursuing offenders*	Removed from the SSP plan to be considered under individual force plans due to differences in processes in this area. Propose to undertake Surrey audit in Q3, and undertake Sussex in either Q4 or 2025/26.
Joint Force Vetting*	Audit cancelled in October due to clash with HMICFRS inspection, along with the Angiolini Inquiry in Sussex examining some of the same areas. Propose to undertake in 2025/26 with a focus on areas for improvements identified by the inspections.
Audit reviews added to the plan
None

Surrey Police Plan
Audit reviews removed from the plan
None
Audit reviews added to the plan
Violence Against Women and Girls - relentlessly pursuing offenders*	Moved from the SSP plan to the Surrey plan due to difference in processes between Surrey and Sussex.